## Jira_web_app_backlog
Work Item ID | Parent ID | Work Type | Summary | Description | Epic Name | Epic Link | Priority | Labels | Story Points | Acceptance Criteria | Sprint | Depends On | Due Date
WEB-001 |  | Epic | Identity, Access & Account Management | Deliver secure account lifecycle, authentication, authorization, and profile management. | EPIC-ACCESS |  | High | web-app,backlog
WEB-002 |  | Epic | Product Experience & Core Workflows | Deliver the application shell and core record-management workflows with responsive, accessible UX. | EPIC-UX |  | High | web-app,backlog
WEB-003 |  | Epic | Platform, API & Data Foundation | Establish API conventions, database integrity, configuration, and operational foundations. | EPIC-DATA |  | High | web-app,backlog
WEB-004 |  | Epic | Quality Engineering & Accessibility | Provide automated coverage, accessibility checks, performance validation, and release confidence. | EPIC-QUALITY |  | High | web-app,backlog
WEB-005 |  | Epic | Delivery, Observability & Production Readiness | Create repeatable build/deploy workflows and enough observability and documentation to operate the service. | EPIC-RELEASE |  | High | web-app,backlog
WEB-006 |  | Story | Register an account and verify email | As a visitor, I want to register and verify my email so that I can create a trusted account. |  | EPIC-ACCESS | High | web-app | 5 | Given valid registration details, when I submit the form, an account is created in an unverified state and a verification message is sent. Invalid inputs show field-level errors. Expired or reused verification links are rejected with a recoverable message.
WEB-007 | WEB-006 | Sub-task | Design registration and verification states | Define form fields, validation messages, loading/success/error states, and responsive layout. |  |  | High | web-app
WEB-008 | WEB-006 | Sub-task | Build registration UI and client validation | Implement accessible form, password rules, pending state, and server-error presentation. |  |  | High | web-app
WEB-009 | WEB-006 | Sub-task | Implement registration endpoint and persistence | Validate payload server-side, hash password using approved library, enforce unique email, and persist unverified account. |  |  | High | web-app
WEB-010 | WEB-006 | Sub-task | Implement verification token and email delivery | Issue expiring single-use token, send verification message through configured provider, and handle invalid/expired token. |  |  | High | web-app
WEB-011 | WEB-006 | Sub-task | Add registration tests | Test happy path, duplicate email, invalid fields, expired token, and verification success. |  |  | High | web-app
WEB-012 |  | Story | Sign in and sign out securely | As a registered user, I want to sign in and sign out so that I can access my account securely. |  | EPIC-ACCESS | High | web-app | 5 | Valid credentials create an authenticated session. Invalid credentials return a generic error. Protected routes reject unauthenticated users. Signing out invalidates the session and returns the user to a public page.
WEB-013 | WEB-012 | Sub-task | Build sign-in and sign-out interactions | Implement sign-in form, disabled/loading states, generic error message, and sign-out action. |  |  | High | web-app
WEB-014 | WEB-012 | Sub-task | Implement authentication and session lifecycle | Validate credentials, establish and revoke sessions/tokens, and apply secure cookie/token settings. |  |  | High | web-app
WEB-015 | WEB-012 | Sub-task | Protect authenticated routes and API endpoints | Enforce authentication at both UI routing and server authorization boundaries. |  |  | High | web-app
WEB-016 | WEB-012 | Sub-task | Add authentication security tests | Cover invalid credentials, session expiry, logout invalidation, and access to protected resources. |  |  | High | web-app
WEB-017 |  | Story | Reset forgotten password | As a user, I want to reset a forgotten password so that I can regain account access. |  | EPIC-ACCESS | High | web-app | 5 | A reset request does not reveal whether an email exists. Reset links expire and are single-use. A successful reset updates the password and invalidates relevant existing sessions according to the security policy.
WEB-018 | WEB-017 | Sub-task | Build password reset screens | Create request-reset and set-new-password screens with validation and clear status messaging. |  |  | High | web-app
WEB-019 | WEB-017 | Sub-task | Implement reset token workflow | Generate random expiring single-use tokens, store safely, and send reset emails. |  |  | High | web-app
WEB-020 | WEB-017 | Sub-task | Enforce password policy and session invalidation | Validate new password server-side and revoke existing sessions as required. |  |  | High | web-app
WEB-021 | WEB-017 | Sub-task | Test password reset abuse and edge cases | Test unknown emails, expired/reused tokens, weak passwords, and successful reset. |  |  | High | web-app
WEB-022 |  | Story | Manage profile details | As a signed-in user, I want to view and update my profile so that my information stays current. |  | EPIC-ACCESS | Medium | web-app | 3 | The profile page displays the current user's permitted fields. Valid edits persist after refresh. Invalid fields show clear errors. Users cannot view or update another user's profile by changing a URL or request payload.
WEB-023 | WEB-022 | Sub-task | Build profile view and edit form | Display profile data and provide accessible edit/cancel/save behavior. |  |  | Medium | web-app
WEB-024 | WEB-022 | Sub-task | Implement profile read/update API | Validate fields and scope reads/updates to the authenticated user. |  |  | Medium | web-app
WEB-025 | WEB-022 | Sub-task | Test profile authorization and validation | Cover valid updates, invalid values, and attempts to access another user's profile. |  |  | Medium | web-app
WEB-026 |  | Story | Manage roles and permissions | As an administrator, I want role-based access controls so that restricted actions are available only to authorized users. |  | EPIC-ACCESS | High | web-app,security | 8 | Roles and permissions are defined centrally. Restricted API operations enforce permissions server-side. Unauthorized attempts return appropriate status codes and are logged without exposing sensitive data.
WEB-027 | WEB-026 | Sub-task | Define roles and permission matrix | Document roles, permitted actions, default role, and authorization rules. |  |  | High | web-app,security
WEB-028 | WEB-026 | Sub-task | Implement server-side authorization policies | Add reusable permission checks for protected operations and default-deny behavior. |  |  | High | web-app,security
WEB-029 | WEB-026 | Sub-task | Add authorization tests | Test permitted and denied actions for each defined role. |  |  | High | web-app,security
WEB-030 |  | Story | Use responsive application shell and navigation | As a user, I want consistent navigation so that I can move between key areas of the app. |  | EPIC-UX | High | web-app | 3 | Primary navigation works with keyboard and pointer. Current location is indicated. Layout remains usable at supported mobile, tablet, and desktop breakpoints. Unknown routes show a helpful not-found page.
WEB-031 | WEB-030 | Sub-task | Define navigation and page layout | Specify information architecture, navigation labels, and responsive behavior. |  |  | High | web-app
WEB-032 | WEB-030 | Sub-task | Build shared application shell | Implement header, navigation, page container, and reusable layout primitives. |  |  | High | web-app
WEB-033 | WEB-030 | Sub-task | Configure routes and not-found handling | Wire routes, active navigation state, and not-found screen. |  |  | High | web-app
WEB-034 |  | Story | Create a core record | As a user, I want to create a record so that I can manage the application's primary information. |  | EPIC-UX | High | web-app | 5 | Valid data creates a record and displays confirmation or the new detail view. Required fields and formats are validated client- and server-side. Failed requests preserve user input and show a useful error.
WEB-035 | WEB-034 | Sub-task | Define core record schema and validation | Agree required fields, types, constraints, ownership, and validation rules. |  |  | High | web-app
WEB-036 | WEB-034 | Sub-task | Build create-record form | Implement fields, inline validation, submit/loading states, and error recovery. |  |  | High | web-app
WEB-037 | WEB-034 | Sub-task | Implement create endpoint and persistence | Validate input, persist record, and return a documented response. |  |  | High | web-app
WEB-038 | WEB-034 | Sub-task | Test record creation and validation | Cover valid submission, missing fields, malformed values, and persistence. |  |  | High | web-app
WEB-039 |  | Story | View record list and record details | As a user, I want to view records and their details so that I can understand and access stored information. |  | EPIC-UX | High | web-app | 5 | The list displays records the user is authorized to see. Selecting a record opens its details. Empty and error states are distinct. Unauthorized access to a record is denied.
WEB-040 | WEB-039 | Sub-task | Build record list and detail views | Implement list rows/cards, loading/empty/error states, and detail page. |  |  | High | web-app
WEB-041 | WEB-039 | Sub-task | Implement list and detail API endpoints | Return authorized records and record details with consistent response shapes. |  |  | High | web-app
WEB-042 | WEB-039 | Sub-task | Test ownership and visibility rules | Verify users only see records allowed by product access rules. |  |  | High | web-app
WEB-043 |  | Story | Edit and archive records | As a user, I want to edit or archive records so that information remains accurate and obsolete items can be removed from active views. |  | EPIC-UX | Medium | web-app | 5 | Authorized edits persist and are reflected in list/detail views. Archiving requires confirmation and removes the item from active results without unintended permanent deletion. Invalid changes are rejected.
WEB-044 | WEB-043 | Sub-task | Build edit form and archive confirmation | Reuse form patterns, confirm archive action, and show success/error feedback. |  |  | Medium | web-app
WEB-045 | WEB-043 | Sub-task | Implement update and archive endpoints | Validate updates, enforce ownership/permissions, and support archive state. |  |  | Medium | web-app
WEB-046 | WEB-043 | Sub-task | Test edit/archive workflows | Cover successful changes, invalid changes, denied actions, and archived-list behavior. |  |  | Medium | web-app
WEB-047 |  | Story | Search, filter, sort, and paginate records | As a user, I want to search and refine records so that I can find relevant information quickly. |  | EPIC-UX | Medium | web-app | 5 | Keyword search, supported filters, deterministic sorting, and pagination work together. Invalid query parameters are handled safely. Empty results and clearing filters are supported.
WEB-048 | WEB-047 | Sub-task | Define searchable fields and filter behavior | Agree supported fields, filter options, sort order, and pagination defaults/limits. |  |  | Medium | web-app
WEB-049 | WEB-047 | Sub-task | Build search/filter/sort controls | Implement search input, filter controls, sort selection, pagination, and clear-filters action. |  |  | Medium | web-app
WEB-050 | WEB-047 | Sub-task | Implement query, filtering, sorting, and pagination | Validate query parameters and return stable paginated results. |  |  | Medium | web-app
WEB-051 | WEB-047 | Sub-task | Test combinations and edge cases | Cover combined filters, no results, invalid parameters, and page boundaries. |  |  | Medium | web-app
WEB-052 |  | Story | Provide consistent notifications and feedback | As a user, I want clear feedback for important actions so that I know whether an operation succeeded or failed. |  | EPIC-UX | Medium | web-app | 3 | Success, validation, and system-error feedback is consistent and accessible. Messages do not expose stack traces or sensitive details. Notifications can be perceived by assistive technology.
WEB-053 | WEB-052 | Sub-task | Define notification patterns | Specify toast/inline message use, duration, wording, and accessibility behavior. |  |  | Medium | web-app
WEB-054 | WEB-052 | Sub-task | Implement reusable feedback components | Create accessible success/error/info components and wire key workflows. |  |  | Medium | web-app
WEB-055 | WEB-052 | Sub-task | Review error messaging across workflows | Check consistency, accessibility announcements, and safe error content. |  |  | Medium | web-app
WEB-056 |  | Story | Establish API conventions and documentation | As a developer, I want consistent API conventions so that frontend and backend integration is predictable. |  | EPIC-DATA | High | web-app | 3 | Endpoints use consistent status codes and error shape. Request/response contracts are documented. API documentation can be generated or reviewed in the development environment.
WEB-057 | WEB-056 | Sub-task | Define API standards and error schema | Document naming, versioning approach, pagination, validation errors, and status-code conventions. |  |  | High | web-app
WEB-058 | WEB-056 | Sub-task | Implement shared API response/error handling | Add reusable validation and error middleware with safe client-facing messages. |  |  | High | web-app
WEB-059 | WEB-056 | Sub-task | Publish API contract documentation | Document endpoint parameters, response examples, auth requirements, and common errors. |  |  | High | web-app
WEB-060 |  | Story | Design database schema and migrations | As a delivery team, we want controlled schema changes so that data remains consistent across environments. |  | EPIC-DATA | High | web-app | 5 | Core entities and relationships are documented. Migrations can be applied to a clean environment and safely run through the documented deployment process. Required constraints and indexes are present.
WEB-061 | WEB-060 | Sub-task | Model entities, relationships, and constraints | Document entity fields, ownership, uniqueness, deletion/archive behavior, and indexes. |  |  | High | web-app
WEB-062 | WEB-060 | Sub-task | Implement migrations and seed data | Create versioned migrations and non-sensitive development seed data. |  |  | High | web-app
WEB-063 | WEB-060 | Sub-task | Validate migration and rollback procedure | Test migration on a clean database and document recovery strategy. |  |  | High | web-app
WEB-064 |  | Story | Configure environment-specific settings and secrets | As a developer, I want environment configuration separated from code so that deployments are safe and repeatable. |  | EPIC-DATA | High | web-app | 3 | Local, test, staging, and production configuration are documented. Secrets are not committed to source control or exposed in client bundles/logs. Missing required configuration fails safely with actionable diagnostics.
WEB-065 | WEB-064 | Sub-task | Define configuration schema and environment variables | List required settings, defaults, and environment-specific values. |  |  | High | web-app
WEB-066 | WEB-064 | Sub-task | Add configuration validation and secret handling | Validate required settings at startup and use approved secret storage for deployments. |  |  | High | web-app
WEB-067 | WEB-064 | Sub-task | Audit repository for committed secrets | Add ignore rules and scanning/checks appropriate to the repository. |  |  | High | web-app
WEB-068 |  | Story | Define data retention, privacy, and audit requirements | As a product owner, I want data handling rules documented so that the app treats user information responsibly. |  | EPIC-DATA | Medium | web-app | 3 | Data categories, retention expectations, access boundaries, and audit events are documented and reviewed by the appropriate stakeholder before production.
WEB-069 | WEB-068 | Sub-task | Create data inventory and retention proposal | List collected data, purpose, access, retention, and deletion requirements. |  |  | Medium | web-app
WEB-070 | WEB-068 | Sub-task | Review privacy and audit requirements | Confirm applicable requirements with product/security/legal stakeholders as needed. |  |  | Medium | web-app
WEB-071 |  | Story | Automate unit and component tests | As the delivery team, we want fast automated tests so that logic and UI regressions are caught early. |  | EPIC-QUALITY | High | web-app | 5 | Critical validation and business logic have unit coverage. Key UI components have tests for important states. Tests run locally and in CI with deterministic results.
WEB-072 | WEB-071 | Sub-task | Configure test framework and conventions | Set up test runner, fixtures, coverage reporting, and naming conventions. |  |  | High | web-app
WEB-073 | WEB-071 | Sub-task | Add unit tests for core logic | Cover validators, transformation logic, permissions, and error handling. |  |  | High | web-app
WEB-074 | WEB-071 | Sub-task | Add component tests for critical UI | Cover forms, loading/empty/error states, and key interaction behavior. |  |  | High | web-app
WEB-075 |  | Story | Automate API integration and end-to-end tests | As the delivery team, we want critical user journeys tested end to end so that releases do not break core workflows. |  | EPIC-QUALITY | High | web-app | 8 | Automated tests cover registration/sign-in, create/view/edit/archive, search, and authorization. Test data is isolated and repeatable. Failures provide actionable diagnostics.
WEB-076 | WEB-075 | Sub-task | Set up API integration test environment | Provide isolated test configuration, fixtures, and reliable database reset. |  |  | High | web-app
WEB-077 | WEB-075 | Sub-task | Implement API integration test suite | Cover validation, status codes, persistence, and access controls. |  |  | High | web-app
WEB-078 | WEB-075 | Sub-task | Implement end-to-end critical journeys | Automate highest-priority browser workflows and capture useful failure artifacts. |  |  | High | web-app
WEB-079 |  | Story | Meet accessibility and responsive design expectations | As a user, I want the application to be accessible and usable on different devices so that I can complete tasks reliably. |  | EPIC-QUALITY | High | web-app | 5 | Critical journeys are keyboard-operable, form fields have labels, focus is visible, contrast meets the agreed standard, and layouts work at supported breakpoints. Automated findings are reviewed manually.
WEB-080 | WEB-079 | Sub-task | Perform accessibility review | Check semantics, labels, keyboard flow, focus order, contrast, and screen-reader announcements. |  |  | High | web-app
WEB-081 | WEB-079 | Sub-task | Fix accessibility findings | Resolve prioritized issues and add regression coverage where practical. |  |  | High | web-app
WEB-082 | WEB-079 | Sub-task | Test responsive layouts | Validate core journeys at agreed mobile/tablet/desktop widths and fix overflow or unusable controls. |  |  | High | web-app
WEB-083 |  | Story | Validate performance and basic security | As a product owner, I want baseline performance and security checks so that the application is dependable and safer to operate. |  | EPIC-QUALITY | High | web-app,security | 5 | Baseline performance targets are agreed and measured for key pages/endpoints. Dependencies and common security risks are reviewed. Findings are prioritized and critical/high-risk issues are addressed or explicitly accepted before release.
WEB-084 | WEB-083 | Sub-task | Define performance budgets and measure baseline | Agree target devices/network and record key page/API measurements. |  |  | High | web-app,security
WEB-085 | WEB-083 | Sub-task | Run dependency and security checks | Run available dependency scanning and review authentication, authorization, input validation, and sensitive-data handling. |  |  | High | web-app,security
WEB-086 | WEB-083 | Sub-task | Triage and resolve release-blocking findings | Track severity, owners, fixes, and retest results for material findings. |  |  | High | web-app,security
WEB-087 |  | Story | Configure continuous integration quality gates | As a developer, I want automated checks on changes so that broken or low-quality changes are caught before merge. |  | EPIC-RELEASE | High | web-app | 3 | Pull requests trigger lint, tests, and production build. Failures are visible and block merge according to team policy. Build instructions are documented.
WEB-088 | WEB-087 | Sub-task | Create CI pipeline | Configure pipeline for install, lint, unit tests, and production build. |  |  | High | web-app
WEB-089 | WEB-087 | Sub-task | Add quality gates and artifacts | Publish test results and define required checks for merge. |  |  | High | web-app
WEB-090 | WEB-087 | Sub-task | Document local verification commands | Provide concise commands for developers to run the same checks locally. |  |  | High | web-app
WEB-091 |  | Story | Deploy to staging and production with rollback | As the delivery team, I want a repeatable deployment process so that releases are controlled and reversible. |  | EPIC-RELEASE | High | web-app | 5 | A release can be deployed using documented steps or pipeline. Required configuration and migrations are checked. Smoke tests verify key journeys. Rollback steps are documented and rehearsed in a safe environment.
WEB-092 | WEB-091 | Sub-task | Define deployment strategy and environments | Document deployment target, promotion path, approvals, and release ownership. |  |  | High | web-app
WEB-093 | WEB-091 | Sub-task | Implement deployment workflow | Configure deployment, environment variables, and migration ordering. |  |  | High | web-app
WEB-094 | WEB-091 | Sub-task | Add post-deploy smoke checks | Verify health endpoint and core application journeys after deployment. |  |  | High | web-app
WEB-095 | WEB-091 | Sub-task | Document and rehearse rollback | Define rollback triggers and steps, then test in non-production. |  |  | High | web-app
WEB-096 |  | Story | Add structured logging, monitoring, and health checks | As the operations team, I want operational signals so that issues can be diagnosed and service health assessed. |  | EPIC-RELEASE | High | web-app | 5 | Logs are structured and exclude secrets and unnecessary personal data. Health/readiness checks report useful status. Monitoring and alert thresholds are documented for agreed critical signals.
WEB-097 | WEB-096 | Sub-task | Implement structured application logging | Use consistent fields and severity levels; avoid logging credentials, tokens, or sensitive payloads. |  |  | High | web-app
WEB-098 | WEB-096 | Sub-task | Add health and readiness endpoints | Report application/dependency readiness without exposing sensitive internals. |  |  | High | web-app
WEB-099 | WEB-096 | Sub-task | Define dashboards and alert runbook | Document key service signals, alert thresholds, owner, and first-response steps. |  |  | High | web-app
WEB-100 |  | Story | Prepare user and developer documentation | As a user and maintainer, I want concise documentation so that I can use, develop, and support the application. |  | EPIC-RELEASE | Medium | web-app | 3 | User-facing guidance covers the primary workflows. Developer docs explain setup, tests, configuration, deployment, and troubleshooting. Documentation is reviewed against the shipped behavior.
WEB-101 | WEB-100 | Sub-task | Write user getting-started guide | Explain account access and core record workflows with screenshots or examples if available. |  |  | Medium | web-app
WEB-102 | WEB-100 | Sub-task | Write developer setup and troubleshooting guide | Document prerequisites, local setup, test commands, environment variables, and common issues. |  |  | Medium | web-app
WEB-103 | WEB-100 | Sub-task | Review release documentation for accuracy | Validate links, commands, configuration names, and workflow descriptions. |  |  | Medium | web-app