## WBS & Estimates
Web Application — Work Breakdown Structure (WBS)
Complete Epic, Story, Task, and Sub-Task Hierarchy with Estimates andTracking
Work Item ID |  |  |  | Hierarchy Level | Title / Summary | Description / Acceptance Criteria | Story Points | Est. Hours | Status
EPIC-000 |  |  |  | Epic | UI/UX Design and Prototyping | Wireframing, design system, and interactive prototypes |  |  | In Progress
| US-001 |  |  | User Story | ↳ As a designer, I want to create a cohesive Design System | AC: Define typography, color palettes, UI components, and design tokens | 8 |  | Done
|  | TSK-001.1 |  | Task | ↳ Develop Component Library and Style Guide | Figma design system setup with responsive variants | 5 |  | Done
|  |  | SUB-001.1.1 | Sub-Task | • Establish color hierarchy, typography, and icon set | Figma global tokens and accessibility-compliant contrast |  | 8 | Done
|  |  | SUB-001.1.2 | Sub-Task | • Design atomic UI components (Buttons, Inputs, Cards, Modals) | Reusable interactive components in Figma |  | 12 | Done
| US-002 |  |  | User Story | ↳ As a product team, I want wireframes and high-fidelity prototypes for key user flows | AC: End-to-end user flows for Auth, Product Catalog, and Checkout | 13 |  | In Progress
|  | TSK-002.1 |  | Task | ↳ Wireframe and Prototype Core User Journeys | Low and high-fidelity mockups for web and mobile web | 8 |  | In Progress
|  |  | SUB-002.1.1 | Sub-Task | • Map user journeys and create low-fi wireframes | User flow diagrams and skeletal layouts |  | 10 | Done
|  |  | SUB-002.1.2 | Sub-Task | • Create high-fidelity interactive Figma prototype | Clickable prototype for user testing and stakeholder sign-off |  | 16 | In Progress
|  |  | SUB-002.1.3 | Sub-Task | • Conduct usability testing and refine designs based on feedback | 5-user testing session with recorded action items |  | 10 | To Do
EPIC-100 |  |  |  | Epic | User Authentication and Profile Management | Core security, identity management, and user profiles |  |  | In Progress
| US-101 |  |  | User Story | ↳ As a user, I want to sign up and log in securely | AC: Supports Email/Pass and OAuth2, enforces strong password rules | 8 |  | In Progress
|  | TSK-101.1 |  | Task | ↳ Develop Auth Backend Services | REST APIs for registration, login, JWT issuance, password reset | 5 |  | In Progress
|  |  | SUB-101.1.1 | Sub-Task | • Design User database schema (Users, Roles, Tokens) | PostgreSQL tables with migration scripts |  | 6 | Done
|  |  | SUB-101.1.2 | Sub-Task | • Implement JWT token generation and validation middleware | Access and Refresh token handling with expiry |  | 8 | Done
|  |  | SUB-101.1.3 | Sub-Task | • Integrate OAuth2 (Google and GitHub SSO) | Passport/OAuth flow setup |  | 10 | In Progress
|  |  | SUB-101.1.4 | Sub-Task | • Write unit tests for Authentication APIs | >85% code coverage for auth endpoints |  | 6 | To Do
|  | TSK-101.2 |  | Task | ↳ Build Auth Frontend UI Components | Responsive forms with real-time validation | 3 |  | In Progress
|  |  | SUB-101.2.1 | Sub-Task | • Design Login and Registration React components | Clean UI using Tailwind CSS |  | 8 | Done
|  |  | SUB-101.2.2 | Sub-Task | • Implement client-side form validation and error messaging | Yup/Zod form validation |  | 5 | In Progress
|  |  | SUB-101.2.3 | Sub-Task | • Connect React Auth forms to Backend APIs | Axios state integration |  | 5 | To Do
| US-102 |  |  | User Story | ↳ As a user, I want to manage my account profile | AC: Users can edit bio, avatar, and notification settings | 5 |  | To Do
|  | TSK-102.1 |  | Task | ↳ Develop Profile Management Features | Profile updates and avatar upload handling | 5 |  | To Do
|  |  | SUB-102.1.1 | Sub-Task | • Create Profile API endpoint and S3 image upload | Multer/AWS S3 integration for avatars |  | 8 | To Do
|  |  | SUB-102.1.2 | Sub-Task | • Build UI Profile dashboard and Avatar cropper | React component with preview |  | 10 | To Do
EPIC-200 |  |  |  | Epic | Product Catalog and Search System | Browsing, searching, and filtering product inventories |  |  | To Do
| US-201 |  |  | User Story | ↳ As a shopper, I want to search and filter products | AC: Search by keyword, filter by category, price, rating | 13 |  | To Do
|  | TSK-201.1 |  | Task | ↳ Implement Search and Filter Engine | Elasticsearch/Full-text search indexing | 8 |  | To Do
|  |  | SUB-201.1.1 | Sub-Task | • Set up Elasticsearch cluster and product indexing | Configure index mappings and dynamic sync |  | 12 | To Do
|  |  | SUB-201.1.2 | Sub-Task | • Create multi-facet Search API (Price, Brand, Rating) | Paginated REST API |  | 10 | To Do
|  |  | SUB-201.1.3 | Sub-Task | • Implement auto-complete and search suggestions | Elasticsearch completion suggester |  | 6 | To Do
|  | TSK-201.2 |  | Task | ↳ Develop Product Catalog UI | Grid layout, filter sidebar, search bar | 5 |  | To Do
|  |  | SUB-201.2.1 | Sub-Task | • Build responsive Product Grid and Card components | Lazy loading images and skeleton loaders |  | 8 | To Do
|  |  | SUB-201.2.2 | Sub-Task | • Implement multi-select Filter Sidebar with debouncing | Interactive sliders and category checkboxes |  | 8 | To Do
EPIC-300 |  |  |  | Epic | Shopping Cart and Checkout Integration | Order workflow, cart persistence, payment processing |  |  | To Do
| US-301 |  |  | User Story | ↳ As a user, I want to add items to cart and checkout via Stripe | AC: Cart persists across sessions, seamless Stripe payment | 13 |  | To Do
|  | TSK-301.1 |  | Task | ↳ Build Shopping Cart Backend and Redis Cache | Fast, distributed cart management | 5 |  | To Do
|  |  | SUB-301.1.1 | Sub-Task | • Implement Redis session storage for guest/logged-in carts | Cart TTL and auto-sync on login |  | 8 | To Do
|  |  | SUB-301.1.2 | Sub-Task | • Create Cart CRUD APIs and stock validation | Prevent overselling before payment |  | 6 | To Do
|  | TSK-301.2 |  | Task | ↳ Integrate Payment Gateway (Stripe) | Secure payment intent handling and webhook processing | 8 |  | To Do
|  |  | SUB-301.2.1 | Sub-Task | • Integrate Stripe Payment Intents API | Server-side payment verification |  | 10 | To Do
|  |  | SUB-301.2.2 | Sub-Task | • Build Stripe Webhook handler for fulfillment | Order state mutation on `payment_intent.succeeded` |  | 8 | To Do
|  |  | SUB-301.2.3 | Sub-Task | • Build React Stripe Elements Checkout Page | PCI-compliant card input UI |  | 12 | To Do
EPIC-400 |  |  |  | Epic | DevOps, CI/CD and Deployment | Infrastructure, automated testing, and cloud deployment |  |  | In Progress
| US-401 |  |  | User Story | ↳ As a developer, I want automated deployment pipelines | AC: GitHub Actions CI/CD to AWS ECS with zero downtime | 8 |  | In Progress
|  | TSK-401.1 |  | Task | ↳ Configure Docker and Infrastructure as Code | Terraform and Docker containerization | 5 |  | Done
|  |  | SUB-401.1.1 | Sub-Task | • Write Dockerfiles for Frontend and Backend microservices | Multi-stage builds for minimal image size |  | 6 | Done
|  |  | SUB-401.1.2 | Sub-Task | • Create Terraform scripts for AWS ECS, RDS, and CloudFront | Provision VPC, Subnets, and Security Groups |  | 14 | Done
|  | TSK-401.2 |  | Task | ↳ Set up Automated CI/CD Pipelines | Automated test runner and deployment scripts | 3 |  | In Progress
|  |  | SUB-401.2.1 | Sub-Task | • Configure GitHub Actions workflow for linting and tests | Triggers on Pull Request to `main` |  | 6 | Done
|  |  | SUB-401.2.2 | Sub-Task | • Configure ECS automated deployment workflow | Rolling updates on merge to `main` |  | 8 | In Progress
EPIC-500 |  |  |  | Epic | Quality Assurance, Automation and Security Testing | Test strategy, E2E test suites, performance and security audits |  |  | To Do
| US-501 |  |  | User Story | ↳ As a QA engineer, I want automated E2E + API testing suites | AC: Playwright automated test execution on CI/CD for critical paths | 13 |  | To Do
|  | TSK-501.1 |  | Task | ↳ Implement API and E2E Test Automation Framework | Playwright and Postman automated test suites | 8 |  | To Do
|  |  | SUB-501.1.1 | Sub-Task | • Set up Playwright framework with Page Object Model (POM) | TypeScript setup with browser matrix |  | 12 | To Do
|  |  | SUB-501.1.2 | Sub-Task | • Write E2E test scripts for Auth, Catalog, Cart, and Checkout | Automated flows covering happy and edge paths |  | 16 | To Do
|  |  | SUB-501.1.3 | Sub-Task | • Integrate Postman/Newman REST API automated regression suite | API endpoint testing triggered on CI pipeline |  | 8 | To Do
| US-502 |  |  | User Story | ↳ As a security and performance lead, I want load testing and vulnerability scans | AC: Application handles 1,000 concurrent users with <200ms API latency | 8 |  | To Do
|  | TSK-502.1 |  | Task | ↳ Execute Performance, Security and Cross-Browser Audits | k6 load testing, OWASP ZAP security scan, Lighthouse audits | 8 |  | To Do
|  |  | SUB-502.1.1 | Sub-Task | • Conduct k6 load testing on Search and Checkout endpoints | Stress testing up to 1,000 concurrent virtual users |  | 10 | To Do
|  |  | SUB-502.1.2 | Sub-Task | • Perform OWASP security audit and penetration testing | Vulnerability assessment (SQLi, XSS, CSRF, auth bypass) |  | 12 | To Do
|  |  | SUB-502.1.3 | Sub-Task | • Run cross-browser and accessibility (WCAG 2.1 AA) audits | Cross-device testing and Lighthouse performance optimization |  | 8 | To Do

## Summary Dashboard
Executive Summary and Metrics Dashboard
Epic ID | Epic Name | Total Story Points | Total Sub-Task Hours | Est. Sprints (2-wk)
EPIC-000 | UI/UX Design and Prototyping | 34 | 56 | 0.7
EPIC-100 | User Authentication and Profile Management | 26 | 66 | 0.83
EPIC-200 | Product Catalog and Search System | 26 | 44 | 0.55
EPIC-300 | Shopping Cart and Checkout Integration | 26 | 44 | 0.55
EPIC-400 | DevOps, CI/CD and Deployment | 16 | 34 | 0.43
EPIC-500 | Quality Assurance, Automation and Security Testing | 37 | 66 | 0.83
| Grand Total | 128 | 244 | 3.06